## project estimates (WBS)
Phase | level | Task/Activity Name | Description | categories | Cost Estimate (Budget) | Timeframe for cost calcuration | Timeframe for reporting | Approach | Basis of Estimate
Second life
*Work breakdown structure-1. Initial Launch Plan- Finish all kinds of preparation
1 | 1 | 1.1: Resource acquisition | For this phase, the focus is to bring together all the necessary resources needed in order to perform the operation. This includes the HQ, the tools, the electronics for refurbishing, and the hardware to perform the needed actions for the process. During this phase, resources need to be allocated, and also the process flow needs to be defined and tested. This will give enough time and space to make changes, move things around and make sure it works the best. It should be clear in this phase what type of electronics and how we are going to store them, process them and sell them. **we don't add maintaining cost for this preparation section since this the action will be occured after we launch our marketing campaign. | Fundamental | 45K |  | Weekly
|  | 1.1.1 electronics waste collection |  | Materials | 15K | buy-out |  |  | We only need to spent time on finding someone who want to throw the old electronics away, but we don't need to pay fees on collecting these electronics. Thus, the cost of this section focus on renting/ buying a truck. (Btw, we need to pay insurance and gas periodly, but hard to define their cost-timeframe.)
|  | 1.1.1.1. find donars |  |  | 0K
|  | 1.1.1.2. transport |  |  | 10K
|  | 1.1.1.3. Storage |  |  | 5K
|  | 1.1.2 Lease offic (HQ/ marketing) |  | Overhead | 12K | Period (quartarly) |  |  | We need to pay rent monthly. However, the duration of preparation is around 3 months (12 weeks), so we calculate the rent total by quarter.
|  | 1.1.2.1 study research |  |  | 2K
|  | 1.1.2.2 allocate money |  |  | 0K
|  | 1.1.2.3 rent office |  |  | 10K
|  | 1.1.3 Permits & Licenses |  | Overhead | 5K | Period (quartarly) |  |  | We need to pay permits & licenses monthly. However, the duration of preparation is around 3 months (12 weeks), so we calculate the rent total by quarter.
|  | 1.1.3.1. Contact lawer |  |  | 2K
|  | 1.1.3.2. pay fees |  |  | 2K
|  | 1.1.3.3. register |  |  | 1K
|  | 1.1.4 IT & Software |  | Materials | 2K | buy-out |  |  | Since we ask requests to oursourcing team, so we define the cost-timeframe is one-time. However, we need to re-calcuate after finishing all kinds of praparation, since periodly maintaining is important for us to keep our quality of service.
|  | 1.1.4.1. Outsource internal management software |  |  | 1.5K
|  | 1.1.4.2. Test IT operations |  |  | 0.5K
|  | 1.1.5 Tools & Hardware |  | Materials | 10K | buy-out
|  | 1.1.5.1 Buy equipment |  |  | 9.5K
|  | 1.1.5.2. Set up equipment |  |  | 0.5K
|  | 1.1.6. Marketing |  | Business | 3K | buy-out
|  | 1.1.6.1 Outsource website |  |  | 2K
|  | 1.1.6.2 Marketing plan |  |  | 1K
2 | 1 | 1.2 HR& Training | The second phase will focus on the hiring and training of human resources. We have different roles to cover, such as technician, sales representative, and volunteers. During the training and before signing off the phase, there has to be a work plan and flow with each employee's role and function, as well as their success criteria. During this training is the perfect time to perform team-building activities as well as implement needed changes in order to work more efficiently before moving into the HQ. | Labor | 12K |  | Weekly
|  | 1.2.1 Hiring |  |  | 10K | Period (quartarly) |  |  | We care about our staffs' working effciency and prodctivity, so we wish they can improve continually through training and KPI evalution. That is to say, we will invest on them periodly.
|  | 1.2.1.1 Search post job offering |  |  | 4K
|  | 1.2.1.2 Research candidates/ market |  |  | 3K
|  | 1.2.1.3 interview |  |  | 3K
|  | 1.2.2 training |  |  | 1K | Period (quartarly)
|  | 1.2.2.1. plan training |  |  | 0.2K
|  | 1.2.2.2. allocate training materials |  |  | 0.2K
|  | 1.2.2.3. execute |  |  | 0.4K
|  | 1.2.2.4. report |  |  | 0.2K
|  | 1.2.3. Probation/period/test/review |  |  | 1K | Period (quartarly)
|  | 1.2.3.1 lesson learn |  |  | 0.4K
|  | 1.2.3.2 test |  |  | 0.6K
3 | 2 | 1.3 intergation | The last phase's main objective is to bring together the first 2 phases once they are ready. In order to better perform the operation, it would be needed to run different tests, like implementation tests. During this and in an iterative way, we can implement upgrades so we can assure that the process is solid and that everyone and everything (HR and tech equipment) works as best as it can. | Execution & Iteration | 1K |  | Weekly |  | This phase is follow by the former phases, so it would be calculated its cost periodly.
|  | 1.3.1 Teat /pilot |  |  | 0.5K | Period (quartarly)
|  | 1.3.1.1 Departments |  |  | 0.5K
|  | 1.3.2 improvements/ Feedback |  |  | 0.5K | Period (quartarly)
|  | 1.3.2.1 meetings |  |  | 0.5K

## project schedule (milestone) (hidden)
Task/Activity/Name | categories | Cost Estimate (Budget) | Timeframe for reporting | Duration | Buffer | Start | Finish | Predecessor | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43
Second life
*Project milestone
0. Get donations ($60K) for the first month. | Donation |  | Weekly | 31 days |  | Mar. 1st | Mar. 31th | 5
1. Initial Launch Plan- Finish all kinds of preparation | Preparetion |  | Weekly | 84 days | 11 days | Apr. 1st | Jul. 4th | 10 | bar: W1 to W13
1.1. Resource acquisition | Fundamental | 45K |  | 77 days | 7 days | Apr. 1st | Jun. 23rd | 5 | bar: W1 to W12
1.1.1.-1.1.1. collect 100 collect 100 pc of old electronics. | Materials | 15K |  | 28 days | 7 days | May. 1st | Jun. 4th | 2 | bar: W5 to W8
1.1.2.-1.1.2. Find a working place | Overhead | 12K |  | 35 days | 7 days | May. 1st | Jun. 11th | 2 | bar: W5 to W9
1.1.3.-1.1.3. Obtain all permits | Overhead | 5K |  | 70 days | 7 days | Apr. 1st | Jun. 16th | 2 | bar: W1 to W10
1.1.4.-1.1.5. Equip our company | Materials | 12K |  | 49 days | 7 days | May. 1st | Jun. 23th | 2 | bar: W5 to W11
1.1.6.-1.1.6. Develop/Design our menu | Business | 3K |  | 21 days | 7 days | May. 1st | May. 25th | 2 | bar: W5 to W7
1.2. Hiring and Training | Labor | 12K |  | 70 days | 7 days | Apr. 8th | Jun. 18th | 5 | bar: W2 to W11
1.3. Integration (1.1.+ 1.2.) | Execution | 1K |  | 7 days | 4 days | Jun. 23th | Jul. 4th | 10 | bar: W12
2. launch our frist marketing campaign and start to provide our service. (Serve 100 customers) | Lanuch+Business | 2K | Monthly | 58 days | (not decided yet) | Jul. 5th | Aug. 31st | 10 | bar: W14 to W23
3. Opening up the first brick-and-mortar store (Serve over 2000 customers) | Development | 50K | Quarterly | 100 days | (not decided yet) | (not decided yet) | (not decided yet) | 30
*Work breakdown structure-1. Initial Launch Plan- Finish all kinds of preparation
1.1: Resource acquisition | Fundamental |  | Weekly | 77 days | 7 days | Apr. 1st | Jun. 23rd | 5
1.1.1 electronics waste collection | Materials | 15K | Weekly | 28 days | 7 days | May. 1st | Jun. 4th | 2 | bar: W5 to W8
1.1.1.1. find donars |  | 0K | bar: W5
1.1.1.2. transport |  | 10K | bar: W5 to W8
1.1.1.3. Storage |  | 5K | bar: W5
1.1.2 Lease offic (HQ/ marketing) | Overhead | 12K | Weekly | 35 days | 7 days | May. 1st | Jun. 11th | 2 | bar: W5 to W9
1.1.2.1 study research |  | 2K | bar: W5 to W8
1.1.2.2 allocate money |  | 0K | bar: W5 to W6
1.1.2.3 rent office |  | 10K | bar: W9
1.1.3 Permits & Licenses | Overhead | 5K | Weekly | 70 days | 7 days | Apr. 1st | Jun. 16th | 2 | bar: W1 to W10
1.1.3.1. Contact lawer |  | 2K | bar: W1 to W2
1.1.3.2. pay fees |  | 2K | bar: W3 to W6
1.1.3.3. register |  | 1K | bar: W7 to W10
1.1.4 IT & Software | Materials | 2K | Weekly | 49 days | 7 days | May. 1st | Jun. 23th | 2 | bar: W5 to W11
1.1.4.1. Outsource internal management software |  | 1.5K | bar: W5 to W8
1.1.4.2. Test IT operations |  | 0.5K | bar: W9 to W11
1.1.5 Tools & Hardware | Materials | 10K | Weekly | 28 days | 7 days | May. 1st | Jun. 4th | 2
1.1.5.1 Buy equipment |  | 9.5K | bar: W5 to W6
1.1.5.2. Set up equipment |  | 0.5K | bar: W7 to W8
1.1.6. Marketing | Business | 3K | Weekly | 21 days | 7 days | May. 1st | May. 25th | 2 | bar: W5 to W7
1.1.6.1 Outsource website |  | 2K | bar: W5 to W6
1.1.6.2 Marketing plan |  | 1K | bar: W5 to W7
1.2 HR& Training | Labor | 12K | Weekly | 70 days | 7 days | Apr. 8th | Jun. 18th | 5 | bar: W2 to W11
1.2.1 Hiring |  | 10K | bar: W2 to W10
1.2.1.1 Search post job offering |  | 4K | bar: W2 to W5
1.2.1.2 Research candidates/ market |  | 3K | bar: W2 to W3
1.2.1.3 interview |  | 3K | bar: W6 to W9
1.2.2 training |  | 1K | bar: W8 to W11
1.2.2.1. plan training |  | 0.2K | bar: W8
1.2.2.2. allocate training materials |  | 0.2K | bar: W8 to W9
1.2.2.3. execute |  | 0.4K | bar: W10
1.2.2.4. report |  | 0.2K | bar: W10
1.2.3. Probation/period/test/review |  | 1K
1.2.3.1 lesson learn |  | 0.4K | bar: W11
1.2.3.2 test |  | 0.6K | bar: W11
1.3 intergation | Execution | 1K | Weekly | 7 days | 4 days | Jun. 23th | Jul. 4th | 10
1.3.1 Teat /pilot |  | 0.5K
1.3.1.1 Departments |  | 0.5K | bar: W12
1.3.2 improvements/ Feedback |  | 0.5K
1.3.2.1 meetings |  | 0.5K | bar: W12

## change control (hidden)
change oringinates
change request submitted | 2 person | 1.8
meeting | 3 mon | 5k per month
evaluation
| risk | 1. amount of electronics collected
decision |  | 2. no techinan want to come here for work
3.we can not find the customer to earn more money
register
implemation

## presentation (hidden)
*introduction (video)
*objective
| *high-level Scope | (not including)
pic | 1. WBS
pic | 2. Budget
pic | 3. Milestone
4. Stakeholder
pic | 5. Change control | critial chain
*conclusion